## Slide 1: ASOPOS 2.0 WORKSHOP Bruxelles (17/18 September 2019)
Decision/Actions made by ASOPOS 2.0 Panel
(Status: December 2018)
Goal of Subgroup meeting at AGU-Fall 2018:
Review the actions and decisions made at Geneva at 19 September 2018 and refine the actions into concrete tasks in order to obtain a concrete work/time plan with milestones and deliverables for 2019/early 2020 plus assignments to do the work by the panel members of ASOPOS 2.0.
Anyother issues ?

## Slide 2: ASOPOS 2.0 –Consensus on Actions and Decisions Made (1)
BACKGROUND CURRENT , in relation to TIME RESPONSE (20 min effect) (David, Holger & Gary)
    Accept single value, post-exposure.
    Refine – use JOSIE data
PUMP EFFICIENCY aka “correction at low pressure” (Herman, Tatsumi & Bryan & Roeland)
    Herman’s proposal on right pump efficiencies + calibration functions
    Analysis from Lab. Data by Tatsumi, Bryan & Roeland?
    Calibration functions by Herman)
RADIOSONDE CORRECTIONS (Ryan & Holger)
    Some Work complete, what else?
META-DATA & (DATA FORMATS) (Holger & Jacquie)
SENSING SOLUTIONS (SST) (Herman, David)
    No Big Change but need to do better where time response compromises measurement (SST Experiments/Herman, Roeland) Analysis Jan-June .
    Evaluation of existing laboratory experiments on impact of KBr and Phosphate Buffer concentrations. (Rene-Bryan-Roeland-Richard)

## Slide 3: ASOPOS 2.0 –Consensus on Actions and Decisions Made (2)
SOLUTION VOLUME CORRECTION (Absorption Efficiency) (Rene & Jonathan?:to be asked)>> Experiments Abs.Eff(Vcathode solution)
Review existing SOP/WMO standard (GAW report 2014) (Roeland & Peter)
SOP FOR USED SONDES (Richard)
  Most experience – Boulder, Payerne, EC3 (Canada), Uccle
What about uncertainties?: Measurement plus Overal Uncertainty plus QA-Flag (David)
  Random uncertainty: Yes , systematic uncertainty:
  Recommendation: Paper describing the different random and systematic uncertainties (David)
  Radiosonde pressure/height bias effect– modern RS can be corrected for – resulting random uncertainity goes into overal uncertainty? (David)
  Flagging: Simple code David/Jonathan

## Slide 4: ASOPOS 2.0 –Consensus on Actions and Decisions Made (3)
11. Strategy/Time Table (late 2018-mid 2020)
  AGU-Fall 2018, Washington: Subgroup meeting (9 people)
  Next Panel meeting: Bruxelles 17/18 September 2019
  Quadrennial Ozone Symposium: Mid 2020
Note: Add item of low pump temperature, there should be some recommendation on keep pump temperature at moderate level (e.e. Active heater as Vaisala or passive heating